## 封面
东软睿驰秘密
文档编号：902EVRD22003-D00-COP02-SW-T34-002
AUTOSAR-AP-2111产品研发项目（902EVRD22003）
需求实现跟踪
版本：3.0
日期：2022-5-6
| 编制 | 审核 | 批准
东软睿驰汽车技术（沈阳）有限公司
(版权所有，翻版必究)

## 变更履历
变更履历
修改编号 | 版本 | 修改内容 | 状态 | 修改人/日期 | 审批人/日期
1 | 0.5 | 初始版本 | Draft | 幸朋/2022.3.24
2 | 0.7 | 增加组合相关模块列 | In review | 幸朋/2022.3.24
3 | 1.0 | 审核通过 | Approved | 幸朋/2022.4.25 | 李冰/2022.4.25
4 | 1.5 | 补充“特性在1911版本状态”及“1911版本是否可测试”信息 | Modified | 董名/2022.4.26
5 | 1.7 | 评审版本 | In review | 董名/2022.4.26
6 | 2.0 | 审核通过 | Approved | 董名/2022.4.26 | 李冰/2022.4.26
7 | 2.5 | 删除原24 25行（规范中已删除，2111已删除部分包含了） 第58行SWSID改成SWS_SM_00200 | Modified | 董名/2022.4.28
8 | 2.7 | 评审版本 | In review | 董名/2022.4.28
9 | 3.0 | 审核通过 | Approved | 董名/2022.5.6 | 李冰/2022.5.6
10
11
12
说明：如果一次变更多个Sheet，每个Sheet的变更内容写一行。首次填写可写一行履历，修改内容写新建。

## SM（2111）
NO. | 子模块名称 | 一级特性 | N级特性 | 需求是否明确 | 是否列入开发计划 | SWS ID | SWS Detail | RS ID | 优先级 | 特性在1911版本状态 | 1911版本是否可测试 | 2111V0.5 是否可测试 | 针对部分实现 说明实现哪部分 | 组合相关模块 | 备注
1 |  | 状态同步 |  | N |  | SWS_SM_00500 | {DRAFT} Virtualized/hierarchical State Management State Management shall be able to register to the "Trigger" fields of a supervising State Management instance to receive information about the whole ECU state. | (RS_SM_00200) |  | 变更 |  | no |  |  | 不支持虚拟化
2 |  | 状态同步 |  | N |  | SWS_SM_00501 | {DRAFT} Virtualized/hierarchical State Management internal State State Management shall implement means to calculate its internal States based on information from a supervising State Management instance. | (RS_SM_00200) |  | 变更 |  | no |  |  | 不支持虚拟化
3 |  | 状态管理服务接口 |  | Y | yes | SWS_SM_00020 | InternalState Propagation State Management shall support implementation of multiple instances of TriggerOut with a Notifier field which reflect State Managements internal states thus Application can get State Managements states. | (RS_SM_00004, RS_SM_00005) |  | 不变 | Y | yes |  | CM
4 |  | 状态管理服务接口 |  | Y | yes | SWS_SM_00021 | InternalState Influence State Management shall support implementation of multiple instances of TriggerIn with a Trigger field which affect State Managements internal states thus Application can influence State Managements states. | (RS_SM_00004, RS_SM_00005) |  | 不变 | Y | yes |  | CM
5 |  | 机器状态切换 |  | Y | yes | SWS_SM_00107 | {DRAFT} Disabling of rapid shutdown State Management shall implement means to set the waitingtime to shutdown the machine to the configured value | (RS_SM_00100) | p3 | 新增 |  |  |  | DCM | 可能还会增加上位机节点
6 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00203 | {DRAFT} Start update session State Management shall provide the service interface UpdateRequest to Update and Configuration Management with the method call RequestUpdateSession to check if an update can be performed. | (RS_SM_00100) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
7 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00209 | {DRAFT} Preventing multiple update sessions RequestUpdateSession shall return kNotAllowedMultipleUpdateSessions in case the method RequestUpdateSession is called during an already active Update Session | (RS_SM_00004) | p1 | 新增 |  | yes |  | UCM和CM
8 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00204 | {DRAFT} Persist session status State Management shall persist information about ongoing update session, thus it can be read out after any kind of Machine reset. | (RS_SM_00004) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
9 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00202 | {DRAFT} Reset Execution State Management shall implement the service interface UpdateRequest to Update and Configuration Management with the method call ResetMachine to request a Machine reset. | (RS_SM_00004) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
10 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00205 | {DRAFT} Stop update session State Management shall provide the service interface UpdateRequest to Update and Configuration Management with the method call StopUpdateSession thus it can inform State Management that the update session is finished. | (RS_SM_00004) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
11 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00206 | {DRAFT} prepare update State Management shall provide the service interface UpdateRequest to Update and Configuration Management with the method call PrepareUpdate thus it can request State Management to perform a preparation of the given Function Groups to be updated. | (RS_SM_00004) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
12 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00207 | {DRAFT} prepare verify State Management shall provide the service interface UpdateRequest to Update and Configuration Management with the method call VerifyUpdate thus it can request State Management to perform a verification of the given Function Groups. | (RS_SM_00004) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
13 |  | 功能组状态切换API |  | Y | yes | SWS_SM_00208 | {DRAFT} prepare rollback State Management shall provide the service interface UpdateRequest to Update and Configuration Management with the method call PrepareRollback thus it can request State Management to perform a preparation of the given Function Groups to be rolled back. | (RS_SM_00004) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
14 |  | 功能组状态切换（仲裁） |  | Y | yes | SWS_SM_00101 | {DRAFT} Diagnostic Reset State Management shall implement means to receive reset requests for Diagnostic Addresses from Diagnostic Management. State Management shall carry out the project specific actions for the specific reset type. | (RS_SM_00100) | p3 | 变更 |  |  |  | DCM
15 |  | 功能组状态切换（仲裁） |  | Y | yes | SWS_SM_00104 | {DRAFT} Diagnostic Reset Last Cause Retrieval State Management shall read out the last persisted reset cause when State Management is spawned. This reset cause has to be provided via C++ interface towards Diagnostic Management. | (RS_SM_00100, RS_SM_00101) | p3 | 变更 |  |  |  | DCM
16 |  | 功能组状态切换（仲裁） |  | Y | yes | SWS_SM_00105 | {DRAFT} Diagnostic Reset Last Cause Reset State Management shall reset the last persisted reset cause immediately after State Management has read out the current value. | (RS_SM_00100, RS_SM_00101) | p3 | 变更 |  |  |  | DCM
17 |  | 功能组状态切换（仲裁） |  | N |  | SWS_SM_00300 | {DRAFT} NetworkHandle Configuration State Management shall receive information about NetworkHandles and their associated Function Group States from Machine Manifest. | (RS_SM_00400) |  | 变更 |  |  |  | NM | 未与NM集成
18 |  | 功能组状态切换（仲裁） |  | N |  | SWS_SM_00301 | {DRAFT} NetworkHandle Registration State Management shall register for all NetworkHandles provided by Network Managements which are available from Machine Manifest. | (RS_SM_00400) |  | 变更 |  |  |  | NM | 未与NM集成
19 |  | 功能组状态切换（仲裁） |  | N |  | SWS_SM_00302 | {DRAFT} NetworkHandle to FunctionGroupState State Management shall set Function Groups to the corresponding Function Group State which is configured in the Machine Manifest for the NetworkHandle when it recognizes a change in NetworkHandle value. | (RS_SM_00401) |  | 变更 |  |  |  | NM | 未与NM集成
20 |  | 功能组状态切换 |  | N |  | SWS_SM_00303 | {DRAFT} FunctionGroupState to NetworkHandle State Management shall change the value of NetworkHandle when Function Groups changes its Function Group State and a NetworkHandle is associated to this Function Group State in the Machine Manifest. | (RS_SM_00400) |  | 不变 |  |  |  | NM | 未与NM集成
21 |  | 功能组状态切换 |  | N |  | SWS_SM_00304 | {DRAFT} Network Afterrun State Management shall support means to support ¡¯afterrun¡¯ to switch off related Function Groups or (partial) networks. The timeout value for this ¡¯afterrun¡¯ has to be read from e.g. Machine Manifest. | (RS_SM_00400) |  | 不变 |  |  |  | NM | 未与NM集成
22 |  | 功能组状态切换 |  | Y | yes | SWS_SM_00400 | {DRAFT} Execution Management State Management shall use API of Execution Management to change the State of Machine State or Function Group State of Function Groups. | (RS_SM_00001) |  | 不变 | Y | yes |  | EM
23 |  | 功能组状态切换 |  | Y | yes | SWS_SM_00401 | {DRAFT} Execution Management Results State Management shall evaluate the results of request to Execution Management. Based on the results State Management may do project-specific actions | (RS_SM_00001) |  | 不变 | Y | yes |  | EM
24 |  | 功能组状态切换 |  | Y | yes | SWS_SM_00004 | {DRAFT} Function Group State Change Request Result State Management shall return an appropriate result to the Adaptive Applications and AUTOSAR Adaptive PlatformApplications which has requested a Function Group State change. | (RS_SM_00001) |  | 不变 | Y | yes |  | CM
25 |  | 功能组状态切换 |  | Y |  | SWS_SM_00100 | {DRAFT} Prevent Shutdown due to Diagnostic Session State Management shall not shutdown the system during an active diagnostic session. Therefore State Management has to register to Adaptive Diagnostics to receive information about active diagnostic session | (RS_SM_00100) |  | 不变 | N
26 |  | 功能组校准 |  | N |  | SWS_SM_00005 | {DRAFT} Function Group Calibration Support State Management shall receive information about deactivated Function Groups from calibration data. | (RS_SM_00001, RS_SM_00300) |  | 不变 |  |  |  |  | EM不支持校准
27 |  | 功能组校准 |  | N |  | SWS_SM_00006 | {DRAFT} Function Group Calibration Support State Management shall decline the request of Adaptive Applications and AUTOSAR Adaptive PlatformApplications to change the Function Group State of a Function Group which is not configured to run in this variant. | (RS_SM_00001, RS_SM_00300) |  | 不变 |  |  |  |  | EM不支持校准
28 |  | 功能组和功能组状态配置 |  | Y | yes | SWS_SM_00001 | {DRAFT} Available Function Group (states) State Management shall obtain available Function Groups and their potential states from the Machine Manifest to set-up the Function Group specific state management. | (RS_SM_00001) |  | 不变 | Y | yes
29 |  | 功能组和功能组状态配置 |  | Y | yes | SWS_SM_00003 | {DRAFT} Function Group State Retrieval State Management shall implement functionality to enable Adaptive Applications and AUTOSAR Adaptive Platform Applications to retrieve the Function Group State of Function Groups and State of Machine State | (RS_SM_00001, RS_SM_00004) |  | 不变 | Y | yes
30 |  | 进程至少配置在一个功能组状态下 |  | Y | yes | SWS_SM_CONSTR_00001 | {DRAFT} Existence of State Management At least one Modelled Process with Process.functionClusterAffinity with the value STATE_MANAGEMENT shall be configured to run in each MachineFG state except Off, whenever one such Modelled Process is configured to run in MachineFG state Startup. | (RS_SM_00001) | p2 | 新增 |  | yes |  |  | 此处规范具体含义存疑
31 |  | 机器状态切换 |  | Y | yes | SWS_SM_00106 | {DRAFT} Enabling of rapid shutdown State Management shall implement means to reduce the waitingtime to shutdown the machine as much as possible | (RS_SM_00100) | p3 | 新增 |  |  |  | DCM | 可能还会增加上位机节点
32 |  | 功能组状态切换（仲裁） |  | Y | yes | SWS_SM_00103 | {DRAFT} Diagnostic Reset Last Cause State Management shall provide functionality to persist reset type before Machine reset is carried out. | (RS_SM_00100, RS_SM_00101) | p3 | 新增 |  |  |  | DCM
33 |  | 功能组接口API |  | Y | yes | SWS_SM_91011 | {DRAFT} Name PowerModeMsg Kind STRING Range/Symbol Limit Description On On normal operation. Off Off persist data preparation for shutdown. Suspend Suspend prepare for suspend2ram. | (RS_SM_00004, RS_SM_00001, RS_AP_00150, RS_AP_00122) | p3 | 新增 |  |  |  |  | 新增的数据类型，类、API等
34 |  | 功能组接口API |  | Y | yes | SWS_SM_91012 | {DRAFT} Name PowerModeRespMsg Kind VALUE Range/Symbol Limit Description kDone 0 requested mode sucessfully reached. kFailed 1 requested mode not reached. kBusy 2 cant process requested mode e.g. important things are ongoing. kNotSupported 3 requested mode not supported. | (RS_SM_00004, RS_SM_00001, RS_AP_00150, RS_AP_00122, RS_AP_00142, RS_AP_00119, RS_AP_00125) | p3 | 新增 |  |  |  |  | 新增的数据类型，类、API等
35 |  | 功能组接口API |  | Y | yes | SWS_SM_91014 | {DRAFT} Name DiagnosticResetRespMsg Kind VALUE Range/Symbol Limit Description kDone 0 reset performed sucessfully. kFailed 1 reset not sucessfully performed. kBusy 2 cant perform reset(e.g. important things are ongoing). kNotSupported 3 reset not supported. | (RS_SM_00001, RS_SM_00004, RS_SM_00100, RS_AP_00150, RS_AP_00122, RS_AP_00142, RS_AP_00119, RS_AP_00125) | p3 | 新增 |  |  |  | DCM | 新增的数据类型，类、API等
36 |  | 功能组接口API |  | Y | yes | SWS_SM_91019 | {DRAFT} Name FunctionGroupNameType Kind STRING | (RS_SM_00004, RS_AP_00150, RS_AP_00122) | p3 | 新增 |  |  |  |  | 新增的数据类型，类、API等
37 |  | 功能组接口API |  | Y | yes | SWS_SM_91001 | {DRAFT} Name TriggerIn_{State} Kind ProvidePort Interface TriggerIn | (RS_SM_00004, RS_SM_00005, RS_AP_00150) |  | 不变 | Y | yes |  | CM
38 |  | 功能组接口API |  | Y | yes | SWS_SM_91002 | {DRAFT} Name TriggerOut_{State} Kind ProvidePort Interface TriggerOut | (RS_SM_00004, RS_SM_00005, RS_AP_00150) |  | 不变 | Y | yes |  | CM
39 |  | 功能组接口API |  | Y | yes | SWS_SM_91003 | {DRAFT} Name TriggerInOut_{State} Kind ProvidePort Interface TriggerInOut | (RS_SM_00004, RS_SM_00005, RS_AP_00150) |  | 不变 | Y | yes |  | CM
40 |  | 功能组接口API |  | Y | yes | SWS_SM_91009 | {DRAFT} Name TriggerInOut_{StateGroup} NameSpace ara::sm Field Trigger Type project_specific HasGetter false HasNotifier false HasSetter true Field Notifier Type project_specific HasGetter true HasNotifier true HasSetter false | (RS_SM_00004, RS_SM_00005, RS_AP_00150, RS_AP_00115) |  | 不变 | Y | yes |  | CM
41 |  | 功能组接口API |  | Y | yes | SWS_SM_91016 | {DRAFT} Name UpdateRequest Kind ProvidePort Interface UpdateRequest | (RS_SM_00001, RS_SM_00004, RS_AP_00150) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
42 |  | 功能组接口API |  | Y | yes | SWS_SM_91017 | {DRAFT} Name UpdateRequest NameSpace ara::sm Method ResetMachine FireAnForget false Application Errors kRejected Method StopUpdateSession FireAndForget false Application Errors kRejected Method RequestUpdateSession FireAndForget false Application Errors kRejected kNotAllowedMultipleUpdateSessions Method PrepareUpdate FireAndForget false Parameter functionGroupList Type functionGroupListType Variation Direction IN Application Errors kRejected kPrepareFailed Method VerifyUpdate FireAndForget false Parameter functionGroupList Type functionGroupListType Variation Direction IN Application Errors kRejected kVerifyFailed Method PrepareRollback FireAndForget false Parameter functionGroupList Type functionGroupListType Variation Direction IN Application Errors kRejected kRollbackFailed | (RS_SM_00001, RS_SM_00004, RS_AP_00150, RS_AP_00115, RS_AP_00120, RS_AP_00142, RS_AP_00119, RS_AP_00121) |  | 不变 | Y | yes |  | UCM和CM | 2011已实现
43 |  | 功能组接口API |  | Y | yes | SWS_SM_91020 | {DRAFT} Name PowerMode NameSpace ara::sm Method message Parameter msg Type PowerModeMsg Variation Direction OUT Method event Parameter respMsg Type PowerModeRespMsg Variation Direction OUT | (RS_SM_00001, RS_SM_00004, RS_AP_00150, RS_AP_00115) | p3 | 新增 |  |  |  |  | 新增的数据类型，类、API等
44 |  | 功能组接口API |  | Y | yes | SWS_SM_91015 | {DRAFT} Name DiagnosticReset NameSpace ara::sm Method message Parameter msg Type DiagnosticResetMsg Variation Direction OUT Method event Parameter respMsg Type DiagnosticResetRespMsg Variation Direction OUT | (RS_SM_00001, RS_SM_00004, RS_SM_00100, RS_AP_00150, RS_AP_00115, RS_AP_00121) | p3 | 新增 |  |  |  | DCM | 新增的数据类型，类、API等
45 |  | 功能组接口API |  | N |  | SWS_SM_91004 | {DRAFT} Name NetworkState_{NetworkHandle} Kind RequirePort Interface NetworkState Variation FOR NetworkHandle : MODEL.filterType("NetworkHandle"); | (RS_SM_00004, RS_SM_00400, RS_AP_00150, RS_AP_00115) |  | 新增 |  |  |  | NM | 未与NM集成
46 |  | 功能组接口API |  | Y | yes | SWS_SM_91010 | {DRAFT} Name Code kNotAlloweMultipleUpdateSessions 9 kPrepareFailed 7 kRejected 5 kRollbackFailed 8 kVerifyFailed 6 | (RS_SM_00004, RS_AP_00150, RS_AP_00125, RS_AP_00142, RS_AP_00119, RS_AP_00149) | p3 | 新增 |  |  |  | UCM | 新增的数据类型，类、API等
47 |  | 2111删除的条目
48 |  | 功能组和功能组状态配置 |  |  |  | SWS_SM_00397 | {DRAFT} Function Group State Retrieval State Management shall implement functionality to enable Adaptive Applications and AUTOSAR Adaptive Platform Applications to retrieve the Function Group State of Function Groups and State of Machine State | (RS_SM_00001, RS_SM_00004)
49 |  | 功能组状态切换 |  |  |  | SWS_SM_00396 | {DRAFT} Function Group State Change Request State Management shall implement functionality to enable Adaptive Applications and AUTOSAR Adaptive PlatformApplications to change the Function Group State of Function Groups | (RS_SM_00001, RS_SM_00004)
50 |  | 功能组状态切换（仲裁） |  |  |  | SWS_SM_00201 | {DRAFT} Supervision of Shutdown Prevention When State Management shall not shutdown the system during an active update session State Management shall supervise the duration of the update session with a project-specific timeout, thus the system does not run forever. | (RS_SM_00100) | [6 empty] | 不支持,UCM监控应该由PHM处理
51 |  | 功能组状态切换 |  |  |  | SWS_SM_00402 | {DRAFT} Function Group State Change Results State Management shall provide Function Group States based on the results of Function Group State change requests to Execution Management via its service interface | (RS_SM_00001) | [6 empty] | 不支持，EM不支持服务接口
52 |  | 功能组状态切换 |  |  |  | SWS_SM_00398 | {DRAFT} Function Group State Change Request Result State Management shall return an appropriate result to the Adaptive Applications and AUTOSAR Adaptive PlatformApplications which has requested a Function Group State change. | (RS_SM_00001)
53 |  | 功能组状态切换 |  |  |  | SWS_SM_00399 | {DRAFT} Prevent Shutdown due to Diagnostic Session State Management shall not shutdown the system during an active diagnostic session. Therefore State Management has to register to Adaptive Diagnostics to receive information about active diagnostic session | (RS_SM_00100)
54 |  | 功能组状态切换（仲裁） |  |  |  | SWS_SM_00200 | {DRAFT} Prevent Shutdown during to Update Session State Management shall not shutdown the system during an active update session. Therefore State Management has to register to Update and Config Management to receive information about active update session | (RS_SM_00100)
Note on C2: 如果模块内有子模块，此处填写子模块名称，如果没有不用填写。 比如：CM有S2S、E2E； UCM有UCM Mater和server等
Note on D2: 特性
Note on E2: 子特性
Note on G2: 是否列入当年开发计划
Note on K2: P1：6/30测完版本 P2：9/30测完版本 P3：12/30测完版本
Note on M2: 各版本释放时填写

## Sheet1
2111删除的条目
1 | 功能组和功能组状态配置 | SWS_SM_00397 | (RS_SM_00001, RS_SM_00004) | {DRAFT} Function Group State Retrieval State Management shall implement functionality to enable Adaptive Applications and AUTOSAR Adaptive Platform Applications to retrieve the Function Group State of Function Groups and State of Machine State
2 | 功能组状态切换 | SWS_SM_00396 | (RS_SM_00001, RS_SM_00004) | {DRAFT} Function Group State Change Request State Management shall implement functionality to enable Adaptive Applications and AUTOSAR Adaptive PlatformApplications to change the Function Group State of Function Groups
3 | 功能组状态切换 | SWS_SM_00398 | (RS_SM_00001) | {DRAFT} Function Group State Change Request Result State Management shall return an appropriate result to the Adaptive Applications and AUTOSAR Adaptive PlatformApplications which has requested a Function Group State change.
4 | 功能组状态切换 | SWS_SM_00399 | (RS_SM_00100) | {DRAFT} Prevent Shutdown due to Diagnostic Session State Management shall not shutdown the system during an active diagnostic session. Therefore State Management has to register to Adaptive Diagnostics to receive information about active diagnostic session
| 功能组状态切换（仲裁） | SWS_SM_00200 | (RS_SM_00100) | {DRAFT} Prevent Shutdown during to Update Session State Management shall not shutdown the system during an active update session. Therefore State Management has to register to Update and Config Management to receive information about active update session