## 封面
东软睿驰秘密
文档编号：902EVRD22003-D00-COP02-SW-T34-003
AUTOSAR-AP-2111产品研发项目（902EVRD22003）
需求实现跟踪
版本：2.0
日期：2022-04-25
| 编制 | 审核 | 批准
东软睿驰汽车技术（沈阳）有限公司
(版权所有，翻版必究)

## 变更履历
变更履历
修改编号 | 版本 | 修改内容 | 状态 | 修改人/日期 | 审批人/日期
1 | 0.5 | 2111 RTM初稿 | Draft | 赵金野/2022.3.2
2 | 0.7 | 追加组合相关模块 | In review | 赵金野/2022.3.24
3 | 1.0 | 审核通过 | Approved | 赵金野/2022.4.25 | 李冰/2022.4.25
4 | 1.5 | 修改文档名称，填写特性在1911版本状态列 | Modified | 赵金野/2022.4.26
5 | 1.7 | 评审版本 | In review | 赵金野/2022.4.26
6 | 2.0 | 审核通过 | Approved | 赵金野/2022.4.26 | 李冰/2022.4.26
7
8
9
10
11
12
说明：如果一次变更多个Sheet，每个Sheet的变更内容写一行。首次填写可写一行履历，修改内容写新建。

## TS(2111)
NO. | 子模块名称 | 一级特性 | N级特性 | 需求是否明确 | 是否列入开发计划 | SWS ID | SWS Detail | RS ID | 优先级 | 特性在1911版本状态 | 1911版本是否可测试 | 2111V0.5 是否可测试 | 针对部分实现 说明实现哪部分 | 组合相关模块 | 备注
1 |  | 模块概述 |  | yes | yes | SWS_TS_00202 | ara::tsync::SynchronizedTimeBaseConsumer:: GetRateDeviation shall return the calculated rate deviation of its TBR against the time source it is synchronized to. In case there is no rate deviation calculated yet, the initial rate deviation of 1 shall be returned. | RS_TS_00018 | P2 | 变更 | NO
2 |  | 启动行为 |  | no | yes | SWS_TS_00007 | Characteristics of Time Base Resources shall be initialized as follows: Active Status Flags shall be invalidated. Clock Update Counter shall be set to zero. The User Data is to be deleted. Time Leap information shall be reset. | RS_TS_00009 | P2 | 新增 | NO |  |  |  | update counter在此处之外其他地方没有描述，api中没有相关 上位机不可配Time Leap，但是代码中对应变量可以先有，在初始化时为0，其他时刻不可用
3 |  | 结束行为 |  | yes |  | SWS_TS_00212 | dFor each Time Base configured as Time Master the value of Global Time shall be stored into persistent memory (’TimeBaseProviderToPersistencyMapping. timeBaseProvider’) (see [11]) if persistent storage is required by configuration parameter. | RS_TS_00024 | P4 | 新增 | NO |  |  | PER
4 |  | 从时间基正常操作行为 |  | no |  | SWS_TS_00139 | Monitoring of time leaps to the future shall only be enabled, if a timeLeapFutureThreshold is other than zero and ara::tsync::SynchronizationStatus unequal to kNotSynchronizedUntilStartup. | RS_TS_00009 | P4 | 变更 | NO |  |  |  | time leap相关本年度不实现；规范不明确：没有offset slave time base，但是time provider（master）中有offset provider，那么slave的时间跳跃是相对谁的，不明确。
5 |  |  |  | no |  | SWS_TS_00140 | Monitoring of time leaps to the past shall only be enabled, if a timeLeapPastThreshold is other than zero and ara::tsync::SynchronizationStatus unequal to kNotSynchronizedUntilStartup. | RS_TS_00009 | P4 | 新增 | NO |  |  |  | time leap相关本年度不实现；规范不明确：没有offset slave time base，但是time provider（master）中有offset provider，那么slave的时间跳跃是相对谁的，不明确。
6 |  |  |  | no |  | SWS_TS_00141 | A check for time leaps shall be performed on every successful synchronization with the master clock, but only after the clock has been synchronized once (ara::tsync::SynchronizationStatus unequal to kNotSynchronizedUntilStartup). | RS_TS_00009 | P4 | 变更 | NO |  |  |  | time leap相关本年度不实现；规范不明确：没有offset slave time base，但是time provider（master）中有offset provider，那么slave的时间跳跃是相对谁的，不明确。
7 |  |  |  | no |  | SWS_TS_00027 | If the adjustment made by the resynchronization exceeded the specified threshold values, the corresponding ara::tsync::LeapJump status shall be set: kTimeLeapNone: if no leap jump happend. kTimeLeapFuture: if there has been a jump in time to the future greater than timeLeapFutureThreshold. kTimeLeapPast: if there has been a jump in time to the past greater than timeLeapPastThreshold. | RS_TS_00009 | P4 | 新增 | NO |  |  |  | time leap相关本年度不实现；规范不明确：没有offset slave time base，但是time provider（master）中有offset provider，那么slave的时间跳跃是相对谁的，不明确。
8 |  |  |  | yes | yes | SWS_TS_00064 | The initail value of (ara::tsync::LeapJump shall be kTimeLeapNone) | RS_TS_00009 | P2 | 变更 | NO |  |  |  | 上位机不可配Time Leap，但是代码中对应变量可以先有，初始化部分可以做
9 |  |  |  | no |  | SWS_TS_00028 | Active Time Leap Status (ara::tsync::LeapJump shall be set to kTimeLeapNone), if a consecutive number timeLeapHealing- Counter of synchronizations were all below the Time Leap Future and Past Thresholds. | RS_TS_00009 | P4 | 变更 | NO |  |  |  | timeLeapHealingCounter意义不明确
10 |  |  |  | no |  | SWS_TS_00030 | Each instance of ara::tsync::Synchronized- TimeBaseConsumer shall independetly monitor for a synchronization timeout by measuring the time since that last update and a specified timeout duration in syncLossTimeout. | RS_TS_00009 | P4 | 变更 | NO |  |  |  | time out相关本年度不实现，没有offset slave time base，但是time provider（master）中有offset provider，那么slave的超时是相对谁的，不明确
11 |  |  |  | no |  | SWS_TS_00032 | In case of a monitored timeout (refer [SWS_TS_00030]) the ara::tsync::SynchronizationStatus shall be set to kTimeOut | RS_TS_00009 | P4 | 新增 | NO |  |  |  | time out相关本年度不实现，没有offset slave time base，但是time provider（master）中有offset provider，那么slave的超时是相对谁的，不明确
12 |  |  |  | no |  | SWS_TS_00011 | On a successful update of the Time Base and the SYNC_TO_GATEWAY bit is set, the ara::tsync::SynchronizationStatus shall be set to kSynchToGateway | RS_TS_00009 | P4 | 变更 | NO |  |  |  | Gateway相关定义不明确
13 |  |  |  | yes | yes | SWS_TS_00033 | On a successful update of the Time Base and the SYNC_TO_GATEWAY bit is NOT set, the ara::tsync::SynchronizationStatus shall be set to kSynchronized | RS_TS_00009 | P3 | 新增 | NO |  | Gateway相关不实现，Gateway以外都实现 |  | 成功update直接标志位置位，不考虑Gateway
14 |  | time slave速率修正 |  | yes |  | SWS_TS_00041 | The TBR shall perform Rate Correction measurements to determine its rate deviation if ara::tsync::SynchronizationStatus is set to kSynchronized. The measurement | RS_TS_00002, S_TS_00018 | P4 | 删除 | NO
15 |  |  |  | yes |  | SWS_TS_00042 | The TBR shall perform Rate Correction measurements continuously. The end of a measurement marks the start of the next measurement. The start and end of measurements is always triggered by (and aligned to) the reception of time values for Synchronized or Offset Time Bases | RS_TS_00002, RS_TS_00007, RS_TS_00018, RS_TS_00019 | P4 | 新增 | NO
16 |  |  |  | yes |  | SWS_TS_00043 | During runtime, the Synchronized TBR shall determine the timespan of a Rate Correction measurement on the basis of clock ara::core:- :SteadyClock | RS_TS_00018 | P4 | 变更 | NO
17 |  |  |  | yes |  | SWS_TS_00044 | The TBR shall perform as many simultaneous Rate Correction measurements as configured by the parameter ’TimeSyncCorrection. rateCorrectionsPerMeasurementDuration’. | RS_TS_00018 | P4 | 变更 | NO
18 |  |  |  | no |  | SWS_TS_00045 | Simultaneous Rate Correction measurements shall be started with a defined offset (ton) to yield Rate Corrections evenly distributed over the measurement duration. The value will be calculated according to the following formula | RS_TS_00018 | P4 | 变更 | NO |  |  |  | ton（a defined offset）定义不明确
19 |  |  |  | no |  | SWS_TS_00046 | At the start of a Rate Correction measurement, the Synchronized TBR shall take the time-snapshots TGStart and TOStart in the scope of TSP. | RS_TS_00018 | P4 | 变更 | NO |  |  |  | SWS对slave 速率修正算法的名词定义，比较混乱。
20 |  |  |  | yes |  | SWS_TS_00047 | At the start of a Rate correction measurement, the Offset TBR, shall take the following time-snapshots in the scope of TSP: | RS_TS_00018 | P4 | 新增 | NO
21 |  |  |  | yes |  | SWS_TS_00048 | At the end of the Rate Correction measurement, the Synchronized TBR shall take the following time-snapshots in the scope TSP | RS_TS_00018 | P4 | 变更 | NO
22 |  |  |  | no |  | SWS_TS_00049 | At the end of the Rate Correction measurement, the Offset TBR shall take the following time-snapshots in the scope TSP: | RS_TS_00018 | P4 | 不变 | NO |  |  |  | 规范中提到了offset TBR，在这里想说的是offset slave TBR，但是在API中没有offset slave相关
23 |  |  |  | yes |  | SWS_TS_00050 | At the end of a Rate Correction measurement, the Synchronized TBR shall calculate the resulting correction rate (rrc) according to the following formula: | RS_TS_00018, RS_TS_00019 | P4 | 不变 | NO
24 |  |  |  | yes |  | SWS_TS_00051 | The last rrc value has to be used until a new value is calculated. | RS_TS_00018, RS_TS_00019 | P4 | 不变 | NO
25 |  |  |  | yes |  | SWS_TS_00052 | Offset TBRs shall not perform yet another rate cor-rection, because this is done by the underlying TBR already. | RS_TS_00018, RS_TS_00019 | P4 | 不变 | NO |  |  |  | 规范中提到了offset TBR，在这里想说的是offset slave TBR，但是在API中没有offset slave相关
26 |  |  |  | yes |  | SWS_TS_00053 | On invocation of ara::tsync::SynchronizedTime- BaseConsumer::GetRateDeviation the TBR shall return the calculated rate deviation (i.e. rrc-1) | RS_TS_00018 | P4 | 变更 | NO
27 |  |  |  | yes | yes | SWS_TS_00070 | If no rate deviation rrc has yet been calculated, ara:- :tsync::SynchronizedTimeBaseConsumer::GetRateDeviation shall return 0.0. | RS_TS_00018 | P2 | 变更 | NO
28 |  |  |  | yes |  | SWS_TS_00054 | If a valid correction rate (rrc) has been calculated, the Synchronized TBR shall apply a Rate Correction. | RS_TS_00018, RS_TS_00019 | P4 | 不变 | NO
29 |  |  |  | no |  | SWS_TS_00071 | If a valid correction rate (rorc,) has been calculated, the Offset TBR shall apply a Rate Correction. | RS_TS_00018, RS_TS_00019 | P4 | 变更 | NO |  |  |  | 规范中提到了offset TBR，在这里想说的是offset slave TBR，但是在API中没有offset slave相关
30 |  | Time Consumer 偏差修正（相位修正） |  | yes | yes | SWS_TS_00055 | For Synchronized TBRs, it shall be measured the offset between its local instance of the Time Base and the Global Time Base whenever the Time Base is synchronized in the scope of the function TSP by taking a snapshot of the following values: | RS_TS_00013 | P2 | 变更 | NO |  |  |  | 从55到60，应该是autosar中如何把slave维护的时间基同步到协议栈上的时间，涉及时钟跳变等。
31 |  |  |  | yes | yes | SWS_TS_00056 | dIf the absolute value of the time offset between Global Time Base and local instance of the Time Base (abs(TG - TLSync)) is equal or greater than ’TimeSyncCorrection.offsetCorrectionJumpThreshold’, the TBR shall calculate the corrected time (TL) of its local instance of the Time Base according to the following formula: TL = TG + (TV - TVSync) * rrc | RS_TS_00013, RS_TS_00019 | P2 | 变更 | NO
32 |  |  |  | yes | yes | SWS_TS_00057 | The TBR shall correct absolute time offsets between the Global Time Base and the local instance of the Time Base (abs(TG - TLSync)), which are smaller than the value given by ’TimeSyncCorrection.offsetCorrection- JumpThreshold’ by temporarily applying an additional rate (roc) to rrc. This rate shall be used for the duration defined by parameter ’TimeSyncCorrection.offsetCorrectionAdaptionInterval’. roc is calculated according to the following formula: roc = (TG - TLSync) / (TCorrInt) + 1 | RS_TS_00013, RS_TS_00019 | P2 | 变更 | NO
33 |  |  |  | yes | yes | SWS_TS_00058 | If the absolute time offset between Global Time Base and local instance of the Time Base (abs(TG - TLSync)) is smaller than ’TimeSync- Correction.offsetCorrectionJumpThreshold’, the TBR shall calculate the corrected time (TL) of its local instance of the Time Base within the period of ’ TimeSyncCorrection.offsetCorrectionAdaptionInterval’ according to the following formula: TL = TLSync + (rrc * (TV - TVSync) * roc ) | RS_TS_00013, RS_TS_00019 | P2 | 变更 | NO
34 |  |  |  | yes | yes | SWS_TS_00059 | If the absolute time offset between the Global Time Base and the local instance of the Time Base (abs(TG - TL)) is smaller than TimeSyncCorrection.offsetCorrectionJumpThreshold, the TBR shall calculate the corrected time (TL) of its local instance of the Time Base after the period of TimeSyncCorrection.offsetCorrectionAdaptionInterval as specified in [SWS_TS_00056] | RS_TS_00013 | P2 | 变更 | NO
35 |  |  |  | yes | yes | SWS_TS_00060 | If TimeSyncCorrection.offsetCorrection- JumpThreshold is set to 0, Offset Correction shall be performed by Jump Correction only. | RS_TS_00013 | P2 | 变更 | NO
36 |  | Global Time Masters速率修正 |  | no |  | SWS_TS_00061 | If ’TimeSyncCorrection.allowProviderRateCorrection’ equals true, an invocation of ara::tsync::SynchronizedTimeBase- Provider::SetRateCorrection shall set the rate correction value. Otherwise ara::tsync::SynchronizedTimeBaseProvider::SetRateCorrection shall do nothing and return the error kLimitsExceeded | RS_TS_00018 | P4 | 变更 | NO |  |  |  | kLimitsExceeded未定义
37 |  |  |  | yes |  | SWS_TS_00062 | The TBR shall apply rate correction, if allow- ProviderRateCorrection equals TRUE and a valid rate correction value has been set by ara::tsync::SynchronizedTimeBaseProvider::SetRateCorrection. | RS_TS_00018 | P4 | 变更 | NO |  |  |  | 61-63这几个，不知道咋实现（我们目前TBR和TSP是分开的，TSP是和硬件/系统相关，如果改频率应该直接改硬件/系统的频率，就不用这几条了）
38 |  |  |  | yes |  | SWS_TS_00063 | If the absolute value of the rate correction parameter rateCorrection, which is passed to SetRateCorrection(), is greater than MasterRateDeviationMax, SetRateCorrection() shall set the actually applied rate correction value to either (MasterRateDeviationMax) or (-MasterRateDeviationMax)(depending on sign of rateCorrection). | RS_TS_00018 | P4 | 不变 | NO
39 |  | Notifications of Time Base Consumer |  | yes | yes | SWS_TS_00701 | A registered notifier via ara::tsync::SynchronizedTimeBaseConsumer:: RegisterStatusChangeNotifier shall be invoked, if one of the following content will change: ara::tsync::SynchronizationStatus, ara::tsync::LeapJump or the user data | RS_TS_00021 | P2 | 新增 | NO |  | leapjump相关不实现，其他实现
40 |  |  |  | yes | yes | SWS_TS_00702 | A registered notifier via ara::tsync::SynchronizedTimeBaseConsumer:: RegisterSynchronizationStateChangeNotifier shall be invoked, if ara::tsync::SynchronizationStatus is changing | RS_TS_00009 | P2 | 新增 | NO |  | timeout相关不实现，其他实现
41 |  |  |  | yes |  | SWS_TS_00703 | A registered notifier via ara::tsync::SynchronizedTimeBaseConsumer:: RegisterTimeLeapNotifier shall be invoked, if ara::tsync::LeapJump is changing | RS_TS_00034 | P4 | 新增 | NO |  |  |  | time leap相关本年度不实现
42 |  | Global Time Precision Measurement Support |  | yes |  | SWS_TS_00803 | A registration via shall only be possible for Synchronized Time Bases and Offset Time Bases, for which isSystemWideGlobalTimeMaster is set to FALSE. | RS_TS_00034 | P4 | 新增 | NO
43 |  |  |  | no |  | SWS_TS_00800 | For Synchronized Time Bases, a registered Time-PrecisionMeasurement notifier (via ara::tsync::SynchronizedTimeBaseConRegisterTimePrecisionMeasurementNotifier) shall write the block elements | RS_TS_00034 | P4 | 新增 | NO |  |  |  | glbSeconds glbNanoSeconds timeBaseStatus virtualLocalTimeLow rateDeviation locSeconds locNanoSeconds pathDelay 相关定义规范不明确，缺失上下文解释
44 |  |  |  | no |  | SWS_TS_00801 | For Offset Time Bases, a registered TimePrecision-Measurement notifier (via g dFor Offset Time Bases, a registered TimePrecision- Measurement notifier (via ara::tsync::SynchronizedTimeBaseConsumer::- RegisterTimePrecisionMeasurementNotifier) shall only write the block ele mentsGlbSeconds, GlbNanoSeconds and TimeBaseStatus to the related measure mentrecording table | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 同上
45 |  | Global Time Validation Measurement Support |  | yes |  | SWS_TS_00424 | Everytime a Follow_Up message is received, all parameters defined by ara::tsync::TimeSlaveMeasurementType shall be updated and the function ara::tsync::ConsumerTimeBaseValidationNotification:: SetSlaveTimingData shall be invoked | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 需要和协议连起来做，目前协议里很多内容都是未研究或者使用默认值，实际项目中未遇到应用场景。
46 |  |  |  | yes |  | SWS_TS_00425 | Everytime a Sync message is transmitted, all parameters defined by ara::tsync::TimeMasterMeasurementType shall be updated and the function ara::tsync::ProviderTimeBaseValidationNotification::- SetMasterTimingData shall be invoked | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 需要和协议连起来做，目前协议里很多内容都是未研究或者使用默认值，实际项目中未遇到应用场景。
47 |  |  |  | yes |  | SWS_TS_00426 | After the current Pdelay measurement is finished, i.e.,upon reception of the Pdelay_Resp_Follow_Up message, all parameters defined by ara::tsync::PdelayInitiatorMeasurementType shall be updated and the function ara::tsync::ConsumerTimeBaseValidationNotification::- SetPdelayInitiatorData shall be invoked | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 需要和协议连起来做，目前协议里很多内容都是未研究或者使用默认值，实际项目中未遇到应用场景。
48 |  |  |  | yes |  | SWS_TS_00427 | After the current Pdelay measurement is finished, i.e., upon transmission of the Pdelay_Resp_Follow_Up, all parameters defined by ara::tsync::PdelayResponderMeasurementType shall be updated and the function ara::tsync::ProviderTimeBaseValidationNotification::- SetPdelayResponderData shall be invoked | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 需要和协议连起来做，目前协议里很多内容都是未研究或者使用默认值，实际项目中未遇到应用场景。
49 |  | API Common Data Types |  |  | yes | SWS_TS_01251 | Timestamp using Timestamp = std::chrono::time_point<TimeBase, std::chrono::nanoseconds>; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
50 |  |  |  | yes | yes | SWS_TS_01260 | TimeBasestruct TimeBase {...}; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
51 |  |  |  | yes | yes | SWS_TS_01261 | rep using rep = std::int64_t; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
52 |  |  |  | yes | yes | SWS_TS_01262 | period using period = std::nano; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
53 |  |  |  | yes | yes | SWS_TS_01263 | duration using duration = std::chrono::duration<rep, period>; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
54 |  |  |  | yes | yes | SWS_TS_01264 | time_point using time_point = std::chrono::time_point<TimeBase>; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
55 |  |  |  | yes | yes | SWS_TS_01265 | is_steady constexpr static bool is_steady = false; | RS_AP_00130, RS_TS_00033, RS_TS_00005 | P1 | 新增 | NO | yes
56 |  |  |  | yes | yes | SWS_TS_01051 | LeapJump enum class LeapJump : std::uint32_t {...} | RS_TS_00009 | P1 | 新增 | NO | yes
57 |  |  |  | yes | yes | SWS_TS_01050 | SynchronizationStatus enum class SynchronizationStatus : std::uint32_t {...} | RS_TS_00009 | P1 | 新增 | NO | yes
58 |  | Synchronized TimeBases Provider |  | yes | yes | SWS_TS_01100 | SynchronizedTimeBaseProvider class SynchronizedTimeBaseProvider final {...} | RS_TS_00030 | P1 | 新增 | NO | yes
59 |  |  |  | no | yes | SWS_TS_01101 | class ara::tsync::SynchronizedTimeBaseProvider explicit SynchronizedTimeBaseProvider (const ara::core::Instance Specifier &specifier) noexcept; | RS_TS_00023 | P1 | 新增 | NO | yes |  |  | specifier怎么用，规范没有说明，接口格式上先按规范实现
60 |  |  |  | yes | yes | SWS_TS_01102 | SynchronizedTimeBaseProvider (SynchronizedTimeBaseProvider &&stbc) noexcept; | RS_TS_00023 | P1 | 新增 | NO | yes
61 |  |  |  | yes | yes | SWS_TS_01103 | operator=(SynchronizedTimeBaseProvider &&stbc) | RS_TS_00023 | P1 | 新增 | NO | yes
62 |  |  |  | yes | yes | SWS_TS_01104 | SynchronizedTimeBaseProvider(const SynchronizedTimeBaseProvider &) | RS_TS_00023 | P1 | 新增 | NO | yes
63 |  |  |  | yes | yes | SWS_TS_01105 | operator=(const SynchronizedTimeBaseProvider &) | RS_TS_00023 | P1 | 新增 | NO | yes
64 |  |  |  | yes | yes | SWS_TS_01106 | ~SynchronizedTimeBaseProvider() | RS_TS_00023 | P1 | 新增 | NO | yes
65 |  |  |  | no | yes | SWS_TS_01107 | SetTime(ara::tsync::Timestamp timePoint, ara::core::Span< const ara::core::Byte > user Data={}) | RS_TS_00010, RS_TS_00026 | P1 | 新增 | NO | yes | user data不可设置 |  | 规范不明确： TsyncErr不明确; 规范冲突： kTimeCannotSet和kDaemonConnectionLost定义一样了
66 |  |  |  | no | yes | SWS_TS_01108 | UpdateTime(ara::tsync::Timestamp, ara::core::Span< const ara::core::Byte > userData={}) | RS_TS_00010, RS_TS_00011, RS_TS_00029, RS_TS_00026, RS_TS_00009 | P1 | 新增 | NO | yes | user data不可设置 |  | 规范不明确： TsyncErr不明确; 规范冲突： kTimeCannotSet和kDaemonConnectionLost定义一样了
67 |  |  |  | yes | yes | SWS_TS_01109 | GetCurrentTime() | RS_TS_00026, RS_TS_00005 | P1 | 新增 | NO | yes
68 |  |  |  | no | yes | SWS_TS_01110 | SetRateCorrection(double rateCorrection) | RS_TS_00029, RS_TS_00026, RS_TS_00018 | P2 | 新增 | NO |  |  |  | ara::tsync::TsyncErrorDomain::Errc::k LimitsExceeded不明确
69 |  |  |  | yes | yes | SWS_TS_01111 | GetRateDeviation() | RS_TS_00018 | P2 | 新增 | NO
70 |  |  |  | yes | yes | SWS_TS_01112 | SetUserData(ara::core::Span< const ara::core::Byte > userData) | RS_TS_00029, RS_TS_00026, RS_TS_00015 | P2 | 新增 | NO
71 |  |  |  | yes | yes | SWS_TS_01113 | GetUserData() | RS_TS_00021, RS_TS_00014 | P2 | 新增 | NO
72 |  |  |  | no |  | SWS_TS_01114 | RegisterTimeValidationNotification(ProviderTimeBaseValidationNotification &timeBase ValidationNotification) | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO |  |  |  | timeBaseValidationNotification不明确
73 |  |  |  | no |  | SWS_TS_01115 | UnregisterTimeValidationNotification() | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO |  |  |  | 与SWS_TS_01114为一对API，1114接口实现不了，该接口没有实现意义
74 |  | Offset TimeBase Provider |  | yes |  | SWS_TS_01200 | OffsetTimeBaseProvider class OffsetTimeBaseProvider final {...}; | RS_TS_00030 | P4 | 新增 | NO
75 |  |  |  | yes |  | SWS_TS_01201 | OffsetTimeBaseProvider(const ara::core::InstanceSpecifier &specifier) | RS_TS_00023 | P4 | 新增 | NO
76 |  |  |  | yes |  | SWS_TS_01202 | OffsetTimeBaseProvider(OffsetTimeBaseProvider &&stbc) | RS_TS_00023 | P4 | 新增 | NO
77 |  |  |  | yes |  | SWS_TS_01203 | operator=(OffsetTimeBaseProvider &&stbc) | RS_TS_00023 | P4 | 新增 | NO
78 |  |  |  | yes |  | SWS_TS_01205 | operator=(const OffsetTimeBaseProvider &) | RS_TS_00023 | P4 | 新增 | NO
79 |  |  |  | yes |  | SWS_TS_01206 | ~OffsetTimeBaseProvider() | RS_TS_00023 | P4 | 新增 | NO
80 |  |  |  | no |  | SWS_TS_01207 | SetOffsetTime(ara::tsync::Timestamp timePoint, ara::core::Span< const ara::core::Byte > user Data={}) | RS_TS_00010, RS_TS_00026 | P4 | 新增 | NO |  |  |  | TsyncErrc不明确； offset定义或解释在规范里没有
81 |  |  |  | no |  | SWS_TS_01208 | GetCurrentTime() | RS_TS_00026, RS_TS_00005 | P4 | 新增 | NO |  |  |  | 获取的时间加不加offset，规范不明确
82 |  |  |  | no |  | SWS_TS_01209 | SetRateCorrection(double rateCorrection) | RS_TS_00029, RS_TS_00026, RS_TS_00018 | P4 | 新增 | NO |  |  |  | TsyncErrorDomain不明确
83 |  |  |  | yes |  | SWS_TS_01210 | GetRateDeviation() | RS_TS_00018 | P4 | 新增 | NO
84 |  |  |  | yes |  | SWS_TS_01211 | SetUserData(ara::core::Span< const ara::core::Byte > userData) | RS_TS_00029, RS_TS_00026, RS_TS_00015 | P4 | 新增 | NO
85 |  |  |  | yes |  | SWS_TS_01212 | GetUserData() | RS_TS_00021, RS_TS_00014 | P4 | 新增 | NO
86 |  |  |  | no |  | SWS_TS_01213 | RegisterTimeValidationNotification(ProviderTimeBaseValidationNotification &timeBase ValidationNotification) | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO |  |  |  | timeBaseValidationNotification规范不明确
87 |  |  |  | no |  | SWS_TS_01214 | UnregisterTimeValidationNotification() | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO |  |  |  | 与SWS_TS_01214为一对API，1214接口实现不了，该接口没有实现意义
88 |  | SynchronizedTimeBaseConsumer |  | yes | yes | SWS_TS_01000 | SynchronizedTimeBaseConsumer class SynchronizedTimeBaseConsumer final {...} | RS_TS_00030 | P2 | 新增 | NO
89 |  |  |  | no | yes | SWS_TS_01001 | SynchronizedTimeBaseConsumer(const ara::core::InstanceSpecifier &specifier) | RS_TS_00023 | P2 | 新增 | NO |  |  |  | specifier怎么用，规范不明确，接口格式上先按规范实现
90 |  |  |  | yes | yes | SWS_TS_01002 | ~SynchronizedTimeBaseConsumer() | RS_TS_00023 | P2 | 新增 | NO
91 |  |  |  | yes | yes | SWS_TS_01003 | SynchronizedTimeBaseConsumer(SynchronizedTimeBaseConsumer &&stbc) | RS_TS_00023 | P2 | 新增 | NO
92 |  |  |  | yes | yes | SWS_TS_01004 | operator=(SynchronizedTimeBaseConsumer &&stbc) | RS_TS_00023 | P2 | 新增 | NO
93 |  |  |  | yes | yes | SWS_TS_01005 | SynchronizedTimeBaseConsumer(const SynchronizedTimeBaseConsumer &) | RS_TS_00023 | P2 | 新增 | NO
94 |  |  |  | yes | yes | SWS_TS_01006 | operator=(const SynchronizedTimeBaseConsumer &) | RS_TS_00023 | P2 | 新增 | NO
95 |  |  |  | yes | yes | SWS_TS_01007 | GetCurrentTime() | RS_TS_00026, RS_TS_00005 | P2 | 新增 | NO
96 |  |  |  | yes | yes | SWS_TS_01008 | GetRateDeviation() | RS_TS_00018 | P2 | 新增 | NO
97 |  |  |  | yes | yes | SWS_TS_01009 | GetTimeWithStatus() | RS_TS_00021 | P3 | 新增 | NO |  |  |  | timestatus相关p2实现
98 |  |  |  | yes | yes | SWS_TS_01010 | RegisterStatusChangeNotifier(std::function< void(const SynchronizedTimeBaseStatus &)> notifier) | RS_TS_00034 | P3 | 新增 | NO |  |  |  | notifier规范不明确；timeleap本年度不实现
99 |  |  |  | yes | yes | SWS_TS_01011 | UnregisterStatusChangeNotifier() | RS_TS_00034 | P3 | 新增 | NO |  |  |  | notifier规范不明确；timeleap本年度不实现
100 |  |  |  | yes | yes | SWS_TS_01012 | RegisterSynchronizationStateChangeNotifier(std::function< void(const SynchronizationStatus &)> notifier) | RS_TS_00034 | P3 | 新增 | NO |  |  |  | timeleap本年度不实现
101 |  |  |  | yes | yes | SWS_TS_01013 | UnregisterSynchronizationStateChangeNotifier() | RS_TS_00034 | P3 | 新增 | NO |  |  |  | timeleap本年度不实现
102 |  |  |  | yes |  | SWS_TS_01014 | RegisterTimeLeapNotifier(std::function< void(const SynchronizedTimeBaseStatus &)> notifier) | RS_TS_00034 | P4 | 新增 | NO
103 |  |  |  | yes |  | SWS_TS_01015 | UnregisterTimeLeapNotifier() | RS_TS_00034 | P4 | 新增 | NO
104 |  |  |  | yes |  | SWS_TS_01016 | RegisterTimeValidationNotification | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO
105 |  |  |  | yes |  | SWS_TS_01017 | UnregisterTimeValidationNotification() | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO
106 |  |  |  | yes |  | SWS_TS_01018 | RegisterTimePrecisionMeasurementNotifier(std::function< void(const TimePrecision Measurement &)> notifier) | RS_TS_00034 | P4 | 新增 | NO
107 |  |  |  | yes |  | SWS_TS_01019 | UnregisterTimePrecisionMeasurementNotifier() | RS_TS_00034 | P4 | 新增 | NO
108 |  | SynchronizedTimeBaseStatus |  | yes | yes | SWS_TS_01052 | SynchronizedTimeBaseStatus class SynchronizedTimeBaseStatus final {...}; | RS_TS_00021 | P3 | 新增 | NO
109 |  |  |  | yes | yes | SWS_TS_01057 | SynchronizedTimeBaseStatus(SynchronizedTimeBaseStatus &&) | RS_TS_00021 | P3 | 新增 | NO
110 |  |  |  | yes | yes | SWS_TS_01058 | SynchronizedTimeBaseStatus(const SynchronizedTimeBaseStatus &) | RS_TS_00021 | P3 | 新增 | NO
111 |  |  |  | yes | yes | SWS_TS_01059 | operator=(SynchronizedTimeBaseStatus &&) | RS_TS_00021 | P3 | 新增 | NO
112 |  |  |  | yes | yes | SWS_TS_01060 | operator=(const SynchronizedTimeBaseStatus &) | RS_TS_00021 | P3 | 新增 | NO
113 |  |  |  | yes | yes | SWS_TS_00127 | For objects that correspond to a Synchronized TBR, this method shall return a copy of the same object this method belongs to. | RS_TS_00021 | P3 | 变更 | NO
114 |  |  |  | no |  | SWS_TS_00129 | For objects that correspond to an Offset TBR, the object returned by this method shall contain the related information of the Synchronized TBR associated to the Offset TBR this object corresponds to. | RS_TS_00021 | P4 | 变更 | NO |  |  |  | 没有offset slave；本年度不做offset相关
115 |  |  |  | no |  | SWS_TS_00131 | The creation time of the Offset TBR’s object and the creation time of the Synchronized TBR associated to the Offset TBR this object corresponds to, shall be identical | RS_TS_00021 | P4 | 变更 | NO |  |  |  | 没有offset slave；本年度不做offset相关
116 |  |  |  | yes | yes | SWS_TS_01055 | GetCreationTime() | RS_TS_00021 | P3 | 新增 | NO
117 |  |  |  | yes | yes | SWS_TS_01053 | GetSynchronizationStatus() | RS_TS_00021 | P3 | 新增 | NO
118 |  |  |  | yes |  | SWS_TS_01054 | GetLeapJump() | RS_TS_00021 | P4 | 新增 | NO |  |  |  | timeleap相关本年度不做
119 |  |  |  | yes | yes | SWS_TS_01056 | GetUserData() | RS_TS_00021, RS_TS_00014 | P3 | 新增 | NO
120 |  |  |  | yes | yes | SWS_TS_00120 | In case there are no User Data stored, ara::tsync:- :SynchronizedTimeBaseStatus::GetUserData shall return an empty vector. | RS_TS_00014, RS_TS_00021 | P3 | 变更 | NO
121 |  | C++ Time Validation Interface |  | no |  | SWS_TS_00414 | TimeMasterMeasurementType struct TimeMasterMeasurementType final {...}; | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
122 |  |  |  | no |  | SWS_TS_14140 | preciseOriginTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
123 |  |  |  | no |  | SWS_TS_14141 | syncEgressTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
124 |  |  |  | no |  | SWS_TS_14142 | sequenceId variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
125 |  |  |  | no |  | SWS_TS_00415 | TimeSlaveMeasurementType struct TimeSlaveMeasurementType final {...}; | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
126 |  |  |  | no |  | SWS_TS_14150 | preciseOriginTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
127 |  |  |  | no |  | SWS_TS_14151 | referenceGlobalTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
128 |  |  |  | no |  | SWS_TS_14152 | syncIngressTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
129 |  |  |  | no |  | SWS_TS_14153 | correctionField variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
130 |  |  |  | no |  | SWS_TS_14154 | referenceLocalTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
131 |  |  |  | no |  | SWS_TS_14155 | pDelay variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
132 |  |  |  | no |  | SWS_TS_14156 | sequenceId variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
133 |  |  |  | no |  | SWS_TS_00416 | PdelayInitiatorMeasurementType struct PdelayInitiatorMeasurementType final {...} | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
134 |  |  |  | no |  | SWS_TS_14160 | requestOriginTimestamp variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
135 |  |  |  | no |  | SWS_TS_14161 | responseReceiptTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
136 |  |  |  | no |  | SWS_TS_14162 | requestReceiptTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
137 |  |  |  | no |  | SWS_TS_14163 | responseOriginTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
138 |  |  |  | no |  | SWS_TS_14164 | referenceLocalTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
139 |  |  |  | no |  | SWS_TS_14165 | referenceGlobalTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
140 |  |  |  | no |  | SWS_TS_14166 | pDelay variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
141 |  |  |  | no |  | SWS_TS_14167 | sequenceId variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
142 |  |  |  | no |  | SWS_TS_00417 | PdelayResponderMeasurementType struct PdelayResponderMeasurementType final {...}; | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
143 |  |  |  | no |  | SWS_TS_14170 | requestReceiptTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
144 |  |  |  | no |  | SWS_TS_14171 | responseOriginTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
145 |  |  |  | no |  | SWS_TS_14172 | referenceLocalTimestamp variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
146 |  |  |  | no |  | SWS_TS_14173 | referenceGlobalTimestamp variable | RS_TS_00034 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
147 |  |  |  | no |  | SWS_TS_14174 | sequenceId variable | RS_TS_00034 | P4 | 删除 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
148 |  |  |  | no |  | SWS_TS_00419 | ProviderTimeBaseValidationNotification class ProviderTimeBaseValidationNotification {...}; | RS_TS_00034, RS_TS_00029 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
149 |  |  |  | no |  | SWS_TS_00423 | SetPdelayResponderData(const PdelayResponderMeasurementType &measurementData) | RS_TS_00034, RS_TS_00029 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
150 |  |  |  | no |  | SWS_TS_00421 | SetMasterTimingData(const TimeMasterMeasurementType &measurementData) | RS_TS_00034, RS_TS_00029 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
151 |  |  |  | no |  | SWS_TS_00428 | ConsumerTimeBaseValidationNotification class ConsumerTimeBaseValidationNotification {...}; | RS_TS_00034, RS_TS_00030 | P4 | 变更 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
152 |  |  |  | no |  | SWS_TS_00422 | SetPdelayInitiatorData(const PdelayInitiatorMeasurementType &measurementData) | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
153 |  |  |  | no |  | SWS_TS_00420 | SetSlaveTimingData(const TimeSlaveMeasurementType &measurementData) | RS_TS_00034, RS_TS_00030 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
154 |  | C++ Time Precision Interface |  | no |  | SWS_TS_01400 | TimePrecisionMeasurement struct TimePrecisionMeasurement final {...}; | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
155 |  |  |  | no |  | SWS_TS_01401 | glbSeconds variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
156 |  |  |  | no |  | SWS_TS_01402 | glbNanoSeconds variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
157 |  |  |  | no |  | SWS_TS_01403 | timeBaseStatus variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
158 |  |  |  | no |  | SWS_TS_01404 | virtualLocalTimeLow variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
159 |  |  |  | no |  | SWS_TS_01405 | rateDeviation variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
160 |  |  |  | no |  | SWS_TS_01406 | locSeconds variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
161 |  |  |  | no |  | SWS_TS_01407 | locNanoSeconds variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
162 |  |  |  | no |  | SWS_TS_01408 | pathDelay variable | RS_TS_00034 | P4 | 新增 | NO |  |  |  | 如SWS_TS_00800，SWS_TS_00801备注所示，SWS中缺失上下文解释，需要参考802.1AS标准文档
Note on C2: 如果模块内有子模块，此处填写子模块名称，如果没有不用填写。 比如：CM有S2S、E2E； UCM有UCM Mater和server等
Note on D2: 特性
Note on E2: 子特性
Note on G2: 是否列入当年开发计划
Note on K2: P1：6/30测完版本 P2：9/30测完版本 P3：12/30测完版本
Note on M2: 各版本释放时填写